## Sheet1
Member | Responsibility | Start Date | Extra
1) Sabin Maharjan (Leader). | i) Code: a) Front End: 1) 20 MCQ of Science and Math. 2) Compile all MCQs and pickle them. 3) Unpickled and Separating the MCQ into Question, Answer and Choice lists. 4) Supply the MCQ to the Interface. 5) Check the answer and keep track of the score. 6) Leaderboard showing top 10 highest scoring users. 7) Sound for correst & incorrect answer and highest score. b) Back End: 1) Insert data from Sign Up Interface. 2) Read and assign data after successful Sign In Interface. 3) Update score of the topic if greater than the score of the database. c) Compiled and Completed the Front End portion. d) Compiled and Completed the Back End portion. e) Compiled and Completed Final Application. ii) Documentation: 1) Testing. 2) Version Control. 3) System Architecture. 4) Project Plan. iii) Error/Exception Handling. iv) Persistent Storage. v) Video. | a: 1) 17 August. 2) 17 August. 3) 17 August. 4) 17 August. 5) 17 August. 6) 28 August. 7) 29 August. b: 1) 26 August. 2) 26 August. 3) 26 August. c) 2 September. d) 7 September. e) 8 September. | 1) Work Division for the code & documentation part. 2) Creating repository in GitHub and assign a branch for each member. 3) Coordination & communication among the members. 4) Code revisoin and suggestions of other members. 5) Reporting and documenting progress.
2) Bishal Shrestha. | Code: 1) 20 MCQ of Sport and Lab. 2) Sign In Interface. 3) Sign Up Interface. Documentation: 1) Development Methodology. 2) Tools and Technology. 3) Conceptual Diagram. 4) Prototype. 5) Developed System. 6) Reference. 7) Compiling and completing whole documentation. | 1) 19 August. 2) 21 August. 3) 24 August. | 1) Supervising Documentation.
3) Abhinav Dev Bhatta. | Code: 1) 20 MCQ of Architecture and GK. 2) Interface for the user: a) Start window. b) Choose topic window. c) Display MCQ and choosing an option. Documentation: 1) Introduction. 2) Aim. 3) Objectives. 4) Features and Functionality. 5) Scope of the project. | 1) 31 August. 2) a) 23 August. b) 26 August. c) 26 August.
4) Aditya Bharti. | Code: 1) 20 MCQ of Programming and Politics. 2) Database: a) Create Database. b) Delete the current user data from the database. Documentation: 1) Conclusion. 2) Appendix. | 1) 17 August. 2) a) 30 August. b) 30 August.